{"text_format":"2","workbook":"xlsx","n_sheets":5,"sheets":["验收工作计划","软件、平台","硬件，设备","集成， 部署","文档"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"验收工作计划","index":0,"n_rows":23,"n_cols":19,"rows_kept":23,"cut":false,"hidden":false,"merged":[[1,1,1,19]]}
[]
[null,"临邑农业项目验收工作计划"]
[{"$nulls":4},"负责人","18号","19号","20号","21号","22号","23号","24号","25号","26号","27号","28号","29号","30号","31号"]
[null,1,"一、软件/平台","农业大数据平台功能，界面调整","张奎、张文娟、林兼丞"]
[null,2,null,"农业溯源平台功能，界面调整","张奎、张文娟、林兼丞"]
[null,3,null,"移动端小程序界面，功能调整","张奎、张文娟、林兼丞"]
[null,4,null,"可视化大屏开发","张奎、张文娟、林兼丞"]
[null,5,"二、硬件/集成","物联网设备采购","李乔伟、罗欢鑫"]
[null,6,null,"服务器部署，虚拟化配置","罗欢鑫"]
[null,7,null,"网络设备配置，网络部署","李乔伟"]
[null,8,null,"物联网设备安装，部署","李乔伟"]
[null,9,null,"农业平台部署上线","罗欢鑫、张奎"]
[null,10,"三、用户培训","培训计划","林兼丞、王珊珊"]
[null,11,null,"培训实施","王珊珊、张文娟、林兼丞"]
[null,12,"四、文档/资料","项目招投标","林兼丞"]
[null,13,null,"产品设计文档","张文娟"]
[null,14,null,"开发技术文档","张奎"]
[null,15,null,"测试文档","王珊珊"]
[null,16,null,"部署和集成","李乔伟、罗欢鑫"]
[null,17,null,"运维","李乔伟、罗欢鑫"]
[null,18,null,"培训","王珊珊、林兼丞"]
[null,19,null,"设备厂商文档汇集","李乔伟、林兼丞、朱景伟"]
[null,20,null,"验收相关","林兼丞"]

{"sheet":"软件、平台","index":1,"n_rows":83,"n_cols":8,"rows_kept":83,"cut":false,"hidden":false,"merged":[[31,1,82,1],[53,2,58,2],[3,2,18,2],[11,3,12,3],[13,3,18,3],[19,2,26,2],[19,3,23,3],[24,3,26,3],[27,2,30,2],[34,2,36,2],[37,2,40,2],[3,1,30,1],[31,2,33,2],[3,3,7,3],[8,3,10,3],[79,2,82,2],[41,2,46,2],[59,2,65,2],[66,2,72,2],[73,2,75,2],[76,2,78,2],[47,2,52,2]]}
[]
[]
[{"$nulls":5},"是否完成","是否测试","说明"]
[null,"智慧农业大数据平台","平台基础管理系统","园区基础模块","企业备案信息服务","是"]
[{"$nulls":4},"检测服务","是"]
[{"$nulls":4},"权限管理","是"]
[{"$nulls":4},"信息发布管理","是"]
[{"$nulls":4},"用户管理","是"]
[null,null,null,"流媒体服务管理模块","下载管理","否",null,"(需要在客户端安装海康的软件)"]
[{"$nulls":4},"查询管理","是"]
[{"$nulls":4},"对接服务","是"]
[null,null,null,"智能集控服务模块","物联网设备管理","是"]
[{"$nulls":4},"终端设备管理","是"]
[null,null,null,"园区综合业务管理模块","新闻资讯","是"]
[{"$nulls":4},"招商引资","是"]
[{"$nulls":4},"溯源查询","是"]
[{"$nulls":4},"园区介绍","是"]
[{"$nulls":4},"园区导航","是"]
[{"$nulls":4},"园区公告","是"]
[null,null,"平台数据挖掘分析系统","农产品数据统计分析模块","价格分析","是"]
[{"$nulls":4},"病虫害分析","是"]
[{"$nulls":4},"生产统计与分析","是"]
[{"$nulls":4},"流向统计与分析","是"]
[{"$nulls":4},"对接服务","是"]
[null,null,null,"投入品数据统计分析模块","农药统计与分析","否"]
[{"$nulls":4},"化肥统计与分析","否"]
[{"$nulls":4},"对接服务","否"]
[null,null,"可视化大屏","GIS地图展示",null,null,null,"开发中，外部资源"]
[null,null,null,"业务数据展示",null,null,null,"开发中，外部资源"]
[null,null,null,"统计数据展示",null,null,null,"开发中，外部资源"]
[null,null,null,"对接服务",null,null,null,"开发中，外部资源"]
[null,"农产品质量安全追溯平台","农产品质量安全监管中心系统","异常监管",null,null,null,"合并到其他模块，没有单独的子系统"]
[null,null,null,"预警管理",null,"否",null,"合并到其他模块，没有单独的子系统"]
[null,null,null,"接口管理"]
[null,null,"农产品生产管理中心系统","生产过程监管",null,"否",null," 补页面"]
[null,null,null,"生产环境监管",null,"否",null," 补页面"]
[null,null,null,"对接服务",null,"否",null," 补页面"]
[null,null,"物流配送管理中心系统","进库量监管",null,"否",null," 补页面"]
[null,null,null,"出库量监管",null,"否",null," 补页面"]
[null,null,null,"运输监管",null,"否",null," 补页面"]
[null,null,null,"对接服务",null,"否",null," 补页面"]
[null,null,"交易信息中心系统","生产交易",null,null,null," 补页面"]
[null,null,null,"物流配送管理中心交易",null,null,null,"补页面"]
[null,null,null,"批发市场交易",null,null,null,"补页面"]
[null,null,null,"农贸市场交易",null,null,null," 补页面"]
[null,null,null,"直营店交易",null,null,null," 补页面"]
[null,null,null,"对接服务"]
[null,null,"农产品生产节点管理子系统","环境管理",null,"是",null,"（有录入功能）"]
[null,null,null,"生产管理",null,"是",null,"农事管理"]
[null,null,null,"投入品管理",null,"是"]
[null,null,null,"交易管理",null,"是"]
[null,null,null,"IC卡管理",null,"否",null,"基础管理没开发完"]
[null,null,null,"对接服务"]
[null,null,"配送中心节点管理子系统","进库管理",null,"是"]
[null,null,null,"出库管理",null,"是",null,"出库就是交易"]
[null,null,null,"运输信息管理",null,"是"]
[null,null,null,"交易管理",null,"是"]
[null,null,null,"IC卡管理",null,"否",null,"加上"]
[null,null,null,"对接服务"]
[null,null,"批发市场节点管理子系统","摊位管理",null,"是"]
[null,null,null,"IC卡管理",null,"是"]
[null,null,null,"进场管理",null,"是"]
[null,null,null,"农药残留检测管理",null,null,null,"未开发"]
[null,null,null,"交易管理",null,"是"]
[null,null,null,"存量管理",null,null,null,"补页面"]
[null,null,null,"对接服务",null,"是"]
[null,null,"农贸市场节点管理子系统","摊位管理",null,"是"]
[null,null,null,"IC卡管理",null,"是"]
[null,null,null,"进场管理",null,"是"]
[null,null,null,"交易管理",null,"是"]
[null,null,null,"存量管理",null,null,null," 补页面"]
[null,null,null,"农药残留检测管理",null,null,null,"未开发"]
[null,null,null,"对接服务",null,"否"]
[null,null,"直营店管理子系统","进货管理",null,"是"]
[null,null,null,"销售管理",null,"是"]
[null,null,null,"对接服务",null,"是"]
[null,null,"终端数据采集节点子系统（移动端）","配送管理"]
[null,null,null,"移动执法"]
[null,null,null,"接口管理"]
[null,null,"追溯查询节点子系统（移动端）","网站查询"]
[null,null,null,"扫码查询"]
[null,null,null,"查询机查询"]
[null,null,null,"接口管理"]

{"sheet":"硬件，设备","index":2,"n_rows":43,"n_cols":10,"rows_kept":43,"cut":false,"hidden":false,"merged":[[38,6,41,6],[2,0,10,0],[12,1,42,1],[12,2,20,2],[12,6,20,6],[21,2,25,2],[21,6,25,6],[26,2,33,2],[26,6,33,6],[34,2,37,2],[34,6,37,6],[38,2,41,2],[11,1,11,2],[2,1,10,1],[2,2,10,2],[2,6,10,6]]}
[]
[null,"类别","项目","项目名称","数量","单位","备注","是否采购到货","备注"]
["基础支撑平台","数据中心","中心平台硬件设备","中心数据库服务器",1,"台","中心机房核心配套设备等","是"]
[null,null,null,"中心应用服务器",1,"台",null,"是"]
[null,null,null,"虚拟化云管软件",2,"套",null,"否","采用kvm开源工具"]
[null,null,null,"流媒体服务器",1,"台",null,"是"]
[null,null,null,"交换机",1,"台",null,"是"]
[null,null,null,"路由器",1,"台",null,"是"]
[null,null,null,"防火墙",1,"台",null,"是"]
[null,null,null,"服务器机柜",1,"台",null,"是"]
[null,null,null,"KVM套件",1,"套",null,"是"]
["农业园大数据展示","可视化展示平台硬件配置",null,"屏体+辅助配置",1,"套","主要包括：55寸液晶拼接屏*12块，落地支架、大屏拼接控制器、配套辅材、电源控制箱、图形拼接处理器、控制主机、线材布设、安装调试、运输等。","是"]
[null,"终端节点硬件设备（生产、加工、流通、销售环节）","种植生产（大棚、基地）示范点","数据集控服务器",5,"台","1个示范点","是"]
[null,null,null,"智能孢子捕捉仪",5,"台",null,"否"]
[null,null,null,"太阳能远程虫情测报站",5,"台",null,"否",null,"带摄像头，球机"]
[null,null,null,"监控摄像机",20,"台",null,"是"]
[null,null,null,"室内温湿度传感器",5,"台",null,"否"]
[null,null,null,"空气CO2传感器",5,"台",null,"否"]
[null,null,null,"光照度传感器",5,"台",null,"否"]
[null,null,null,"土壤温度，水分传感器",5,"台",null,"否"]
[null,null,null,"网络工程改造+网络设备",1,"套"]
[null,null,"农产品加工示范点","电脑",3,"台",null,"是"]
[null,null,null,"溯源码打印机",1,"台",null,"否"]
[null,null,null,"溯源卡读写器",2,"台",null,"否"]
[null,null,null,"流水线改造（溯源码相关）",1,"台"]
[null,null,null,"网络工程改造+网络设备",1,"套"]
[null,null,"批发市场示范点","电脑",1,"台"]
[null,null,null,"票据打印机",1,"台",null,"否"]
[null,null,null,"溯源卡读写器",1,"台"]
[null,null,null,"移动执法终端",1,"台",null,"否"]
[null,null,null,"便携式食品安全快速检测设备",1,"台",null,"否"]
[null,null,null,"大型溯源电子秤",2,"台",null,"否"]
[null,null,null,"手持交易终端",1,"台"]
[null,null,null,"网络工程改造+网络设备",1,"套"]
[null,null,"配送中心示范点","打印纸",1,"套"]
[null,null,null,"手持交易终端",1,"台",null,"否"]
[null,null,null,"溯源码打印机",1,"台"]
[null,null,null,"网络工程改造+网络设备",1,"套"]
[null,null,"直营店示范点","零售溯源电子秤",2,"台",null,"否"]
[null,null,null,"电脑",1,"台"]
[null,null,null,"溯源秤打印纸",1,"套"]
[null,null,null,"溯源查询机",2,"台",null,"否"]
[null,null,"IC卡","溯源IC卡",100,"张","100张","否"]

{"sheet":"集成， 部署","index":3,"n_rows":38,"n_cols":7,"rows_kept":38,"cut":false,"hidden":false,"merged":[[3,2,6,2],[7,2,9,2],[10,2,13,2],[14,2,15,2],[16,2,18,2],[20,2,26,2],[27,2,29,2],[30,2,33,2],[35,2,36,2],[19,2,19,6]]}
[]
[]
[{"$nulls":4},"是否完成","是否测试","说明"]
[null,1,"软件/平台","大数据平台部署（含数据库）"]
[null,2,null,"农产品质量追溯平台部署（含数据库）"]
[null,3,null,"移动执法终端","否"]
[null,4,null,"追溯查询终端","否"]
[null,5,"服务器、机房","机柜安装 1个","是","是"]
[null,6,null,"服务器安装 8台","是","是"]
[null,7,null,"KVM套件安装","是","是"]
[null,8,"网络","交换机安装，配置 1台（含 IP、子网划分）","是","否"]
[null,9,null,"防火墙安装、配置 1台","是","否"]
[null,10,null,"网络布线 ？？？","是","是"]
[null,11]
[null,12,"系统，存储、虚拟化","虚拟化云管系统安装，配置"]
[null,13,null,"服务器系统安装 centOS ??","是","是","预装系统"]
[null,14,"大屏","大屏安装","是","是"]
[null,15,null,"拼接器安装","是","是"]
[null,16,null,"控制软件安装","是","是"]
[null,17,"物理网设备"]
[null,18,"种植生产（大棚，基地）","智能孢子捕捉仪安装  6个点 ","否"]
[null,19,null,"虫情测报站安装  5个点 ","否"]
[null,20,null,"监控摄像机  20个 ","否"]
[null,21,null,"室内温湿度传感器 5个点 ","否"]
[null,22,null,"空气C02传感器 5个点 ","否"]
[null,23,null,"光照传感器 5台 ","否"]
[null,24,null,"土壤温度、水分传感器  5台 ","否"]
[null,25," 农产品加工示范点","电脑 3 台  ","否"]
[null,26,null,"溯源码打印机 1台  ","否"]
[null,27,null,"溯源卡读写器 2台 ","否"]
[null,28,"批发市场示范点","票据打印机 1台  ","否"]
[null,29,null,"移动执法终端  1台 ","否"]
[null,30,null,"便携式食品安全快速检测设备 1台  ","否"]
[null,31,null,"批发电子秤  2台 ","否"]
[null,32," 配送交易中心","手持交易终端 1台","否"]
[null,33,"直营示范点","零售电子秤 2台 ","否"]
[null,34,null,"溯源查询机 2台 ","否"]
[null,35,"IC卡","溯源IC卡 100张","否"]

{"sheet":"文档","index":4,"n_rows":30,"n_cols":4,"rows_kept":30,"cut":false,"hidden":false,"merged":[[0,0,0,3]]}
["临邑农业大数据和农业溯源平台项目验收文档清单"]
[null,"分类","文档","状态"]
[1,"一、招标","招标文件"]
[2,null,"招标公告（附打印的网页）"]
[3,null,"中标结果公告（附打印的网页）"]
[4,null,"中标通知书"]
[5,null,"供应商投标文件"]
[6,null,"采购合同（原件）"]
[7,"二、设计开发","系统需求规格说明书"]
[8,null,"系统概要设计（农业大数据平台，农业溯源平台）前后端"]
[9,null,"详细设计说明书  ？？？"]
[10,null,"数据库设计、数据字典"]
[11,null,"第三方接口说明文档"]
[12,null,"项目源代码"]
[13,"三、测试","功能测试用例"]
[14,null,"功能测试报告"]
[15,null,"性能测试方案、测试计划"]
[16,null,"性能测试报告"]
[17,"四、集成&安装部署&运维","基础支撑环境设计和部署方案"]
[18,null,"基础环境、服务器、网络等资源配置项说明&竣工图（服务器、大屏设备、ip、机柜。。。。）"]
[19,null,"系统安装部署文档"]
[20,null,"设备清单和型号说明（包括各种采购设备的产品说明书）"]
[21,null,"系统运维手册（软件平台的日常运维、数据库维护、 设备的维护、大屏的维护。。。。）"]
[22,"五、培训","用户使用手册（大数据平台、溯源平台、电子秤、查询机、移动终端、大屏）"]
[23,null,"培训计划 ？？？"]
[24,null,"培训教案 ？？？"]
[25,null,"培训记录 ？？？"]
[26,"六、初验","初验申请"]
[27,null,"项目初验总结报告"]
[28,null,"初验评审意见（模板）"]