{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["全年"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"全年","index":0,"n_rows":35,"n_cols":14,"rows_kept":35,"cut":false,"hidden":false,"merged":[[0,0,0,4]]}
["2021年交通设施维修维护工程"]
["时间","施工地点","施工内容","工作井数量\n（个）","管线长度\n（米）","信号机箱基础\n(个)","灯杆基础(个)","挖沟槽土方\n（m³）","挖基础土方\n（m³）","独立基础\n（m³）","挖人行步道\n（平米）","人行道块料铺设\n（平米）","种植草皮\n（平米）","余土弃置（m³）"]
["2021-02-26","左堤路松鹤酒店门口","信号灯杆基础、挖埋管线、砌工作井",1,25,null,1,{"$f":"0.6*0.8*E3","v":12},{"$f":"0.5*0.5*3.14*1.5*D3+0.7*0.7*0.7*F3+2*2*2*G3","v":9.1775},{"$f":"0.7*0.7*0.7*F3+2*2*2*G3","v":8},5,5,{"$f":"E3-K3","v":20},{"$f":"H3+I3+J3","v":29.1775}]
["2021-03-27","顺平南线与木北路","信号灯杆基础、挖埋管线、砌工作井",1,150,null,1,{"$f":"0.6*0.8*E4","v":72},{"$f":"0.5*0.5*3.14*1.5*D4+0.7*0.7*0.7*F4+2*2*2*G4","v":9.1775},{"$f":"0.7*0.7*0.7*F4+2*2*2*G4","v":8},50,50,100,89.1775]
["2021-04-01","怀昌路天北路","信号灯杆基础、挖埋管线",null,75,null,1,36,8,8,15,15,60,52]
["2021-04-02","龙凤路与昌金路","信号灯杆基础、挖埋管线、砌工作井",1,100,null,1,48,9.1775,8,45,{"$f":"K6","v":45},55,65.1775]
["2021-04-08","北务西路","挖筑标志牌基础",{"$nulls":5},0.28,0.28,null,null,0,0.56]
["2021-04-25","马可汇路口","信号机箱基础、挖埋管线、砌工作井",1,50,1,null,24,1.5205,0.343,10,10,40,25.8635]
["2021-04-28","南环路六环入口","挖筑信号灯杆基础、挖埋管线、砌工作井",1,100,null,1,48,9.1775,8,20,20,{"$f":"E9-K9","v":80},{"$f":"H9+I9+J9","v":65.1775}]
["2021-05-09","通顺路与外环路","挖埋管线",null,120,null,null,57.6,0,0,40,40,80,57.6]
["2021-05-24","京沈路与天纬四街","信号机箱基础、挖埋管线",null,null,1,null,0,0.343,0.343,null,null,0,0.686]
["2021-05-26","北石槽西下路与北武路","信号灯杆基础、挖埋管线",1,150,1,null,72,1.5205,0.343,30,30,120,73.8635]
["2021-05-27","京沈路与Y117乡道交叉口","挖埋管线",null,90,null,null,43.2,0,0,30,30,60,43.2]
["2021-05-31","京沈路与官志卷村路口","信号灯杆基础、挖埋管线",1,120,1,null,57.6,1.5205,0.343,40,40,80,59.4635]
["2021-06-09","顺平路与李木路","信号机箱基础、挖埋管线",1,75,1,null,36,1.5205,0.343,15,15,60,37.8635]
["2021-06-17","减河北路与左堤路辅线人行灯","信号灯杆基础、挖埋管线",null,50,null,1,24,8,8,10,10,40,40]
["2021-06-17","火寺路与北木路","挖埋管线",null,200,null,null,96,0,0,200,200,0,96]
["2021-07-20","龙塘路通顺路","信号机箱基础、挖埋管线、砌工作井",2,75,1,null,36,2.698,0.343,15,15,60,39.041]
["2021-08-01","龙塘路与木燕辅线丁字路口","信号灯杆基础、挖埋管线",1,100,null,1,48,9.1775,8,20,20,{"$f":"E19-K19","v":80},{"$f":"H19+I19+J19","v":65.1775}]
["2021-08-18","顺康路石园大街","换信号灯底座",null,null,null,1,0,8,8,0,0,0,16]
["2021-08-29","顺平路李木路","信号灯杆基础、挖埋管线、砌工作井",1,75,null,1,36,9.1775,8,5,5,70,53.1775]
["2021-08-29","石园大街","信号灯杆基础、挖埋管线、砌工作井",9,468,1,6,224.64,58.9405,48.343,156,156,312,331.9235]
["2021-09-09","陈马路与木北路路口","信号灯杆基础、挖埋管线",2,105,null,1,50.4,10.355,8,45,45,60,68.755]
["2021-09-14","八中路口","挖埋管线",null,105,null,null,50.4,0,0,35,35,70,50.4]
["2021-09-17","白马李木路","信号灯杆基础、挖埋管线、砌工作井",1,75,null,1,36,9.1775,8,5,5,70,53.1775]
["2021-09-19","李天路楼台村","挖埋管线",null,240,null,null,115.2,0,0,120,120,120,115.2]
["2021-09-21","昌金路中干渠","信号灯杆基础、挖埋管线、砌工作井",2,60,null,2,28.8,18.355,16,12,12,48,63.155]
["2021-09-22","安宁大街裕华路路口","信号灯杆基础、挖埋管线",null,75,null,1,36,8,8,15,15,60,52]
["2021-09-24","木燕路与东疃村口","信号灯杆基础",null,25,null,1,12,8,8,5,5,20,28]
["2021-09-30","白马路与顺密路路口","信号机箱基础",1,null,1,null,0,1.5205,0.343,0,0,0,1.8635]
["2021-11-27","白马路与木北路","信号灯杆基础、挖埋管线",null,90,null,1,43.2,8,8,0,0,0,59.2]
["2021-12-28","天北路顺平路","信号灯杆基础、挖埋管线",null,100,null,4,48,32,32,0,0,0,112]
["2021-12-28","天北路董各庄路口","信号灯杆基础、挖埋管线",null,25,null,2,12,16,16,0,0,0,44]
[]
[null,null,null,27,{"$f":"SUM(E3:E34)","v":2923},8,28,1403.04,258.8165,227.024,943,943,1765,1888.8805]